## Gantt Chart
iHP Emulator Module - Joint Honours Project Plan
Supervisor Name | Dr Ernesto Compatangelo |  |  | 2019-01-07
Student Name / ID | Sonke Wohler / 51552212 |  |  | 2019-05-03
Task ID | TASK TITLE | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
|  | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-03-03
1 | Inception
1.1 | Finalising Subject Choice
1.2 | Project Outline
1.2.1 | Requirement & Technology Specification
1.3 | Basic Domain Definition
1.4 | Inception Review
2 | Elaboration
2.1 | User Modelling Analysis
2.2 | Architectural Design
2.3 | Specification Review
3 | Experimentation
3.1 | Modular Prototyping
3.2 | Modular Testing
3.3 | Technology Review
3.4 | Prototyping Review
4 | Project Assembly
4.1 | Module Integration
4.2 | Integration Tesing
4.3 | Full Testing Plan Inception
4.4 | Assembly Review
5 | Project Finalisation
5.1 | Full Product Testing
5.2 | Requirement Review
5.3 | Refactoring Review/Plan (for future work)
5.4 | Final Project Review
6 | Presentation
6.1 | Report Finalisation
6.2 | Documentation Finalisation
6.3 | Demonstration Testing
6.4 | Industrial Review
6.5 | Final Review and Submission
6.6 | Presentation | [16 empty] | Presentation Date TBA